## Change_Log
Date | Environment | Org Alias | Component Type | Component Name | API Name | Reason | Before Change Details | After Change Details | Change Summary | Deployment Details | Rollback Details | Testing Details | Salesforce Link
2026-10-08 | Sandbox | FullSando | Flow (Record-Triggered) | Cases disposition | Cases_disposition | To align the Sandbox Case Disposition Flow with the Production configuration. | Flow version 4 (active). Entry conditions: 1. Origin Equals Email; 2. Case Subcategory Is Changed True; 3. Case Subcategory Is Null False; 4. Case Request Is Changed True; 5. Case Request Is Null False. Logic: AND. | Flow version 5. Entry conditions 1-5 unchanged, plus: 6. Status Equals New; 7. Status Equals Assigned; 8. Status Equals In Progress. Logic: 1 AND 2 AND 3 AND 4 AND 5 AND (6 OR 7 OR 8). | Added three status entry conditions, joined with OR. Used the standard Status field by mistake; corrected in version 6 the same day. | Deployment ID 0AfVa00000Df2SzKAJ, 2026-10-08. Deployed and activated as version 5. Superseded by version 6 (now Obsolete). | Setup > Flows > Cases disposition > View Versions > activate version 4. | Not tested. Replaced by version 6 before testing. | https://teamvelocity--fullsando.sandbox.my.salesforce.com/builder_platform_interaction/flowBuilder.app?flowId=301Va000015R2iVIAS
2026-10-08 | Sandbox | FullSando | Flow (Record-Triggered) | Cases disposition | Cases_disposition | To align the Sandbox Case Disposition Flow with the Production configuration. Corrects version 5 to use the Case Status field. | Flow version 5 (active). Entry conditions 1-5 as in version 4, plus 6-8 on the standard Status field = New / Assigned / In Progress. Logic: 1 AND 2 AND 3 AND 4 AND 5 AND (6 OR 7 OR 8). | Flow version 6. Entry conditions 1-5 unchanged, plus: 6. Case Status (Status_Filtered__c) Equals New; 7. Case Status Equals Assigned; 8. Case Status Equals In Progress. Logic: 1 AND 2 AND 3 AND 4 AND 5 AND (6 OR 7 OR 8). | Added filters: Case Status Equals 'New', 'Assigned' and 'In Progress' (field Status_Filtered__c). Routing to the High, Medium and Low Priority Case queues is unchanged. Change record: 2026-10-08_Case_Disposition_Flow_Updates.txt. | Deployment ID 0AfVa00000Df3LqKAJ, 2026-10-08. Validated with a check-only deploy, then deployed and activated as version 6. | Setup > Flows > Cases disposition > View Versions > activate version 4 (original) or version 5. | Not yet tested. Test: update an email case with Case Status New, Assigned or In Progress and change Case Subcategory and Case Request; it should route to the queue for its priority. | https://teamvelocity--fullsando.sandbox.my.salesforce.com/builder_platform_interaction/flowBuilder.app?flowId=301Va000015RMAjIAO

## Instructions
Change Log - how to maintain this workbook
1. Add one new row to the Change_Log sheet for every Salesforce change: metadata, configuration, flow, field, object, validation rule, Apex, LWC, integration, deployment or permission.
2. Never edit or delete existing rows. If a past entry was wrong, add a new row that corrects it and say which entry it corrects.
3. Add new rows at the bottom, in date order. Write dates as YYYY-MM-DD.
4. Fill in every column. Write "Not stated" or "Not tested" rather than leaving a cell blank.
5. Org Alias is the Salesforce org alias the change was made in (for example FullSando).
6. Before Change Details and After Change Details must give the actual values, not just a description.
7. Salesforce Link points to the changed component in the org (Setup page or builder).
8. Commit the updated workbook to Git with a meaningful message. Git history is the audit trail.
Supporting change records (one text file per change) are kept in the same folder: Documentation/04_Change_Records/.